## Sprint1
Sprint Duration: | Week 1
Sprint 1 Goal: | Implement the Home Page code based on the approved wireframe. The team will convert the Home Page wireframe into a working frontend page by creating the required layout sections, styling, navigation, content blocks, responsive design, and initial testing. Sprint 1 is limited only to the Home Page.
Status | Task | Assigned To | Deliverable | Time Estimated | Time Spent | Time Remaining | Support Required | Notes
Complete | Review Home Page wireframe and divide it into frontend sections | Arnob Intishar Chisty | Home Page section breakdown and implementation checklist | 2 | 2 | 0 | Approved Home Page wireframe | Review the wireframe and identify sections to implement: Header, Navigation, Hero Banner, Featured Categories, Product Preview, About/Brand, CTA, Newsletter, and Footer.
Complete | Set up GitHub repository and prepare codebase for Home Page implementation | Arnob Intishar Chisty | GitHub repository setup, project folder structure, initial commit, README update | 2 | 2 | 0 | Team GitHub usernames | Prepare the codebase, push initial files, and ensure team members can access the repository.
Complete | Prepare Home Page content and branding assets | Nazeefa Binta Alam | Home Page text content, logo, images, banner content, navigation labels, brand colors | 3 | 3 | 0 | Client input and wireframe reference | Collect Home Page-only assets: logo, hero title/subtitle, buttons, categories, preview text, promotions, contact/social details, and footer content.
Complete | Implement Header and Navigation section | Nazeefa Binta Alam | Header component with logo, navigation menu, search/cart/account icons or placeholders | 3 | 3 | 0 | Navigation labels and logo | Convert the wireframe header into code with logo area, menu items, navigation links, and basic responsive behavior.
Complete | Implement Hero Section from wireframe | Nazeefa Binta Alam | Hero banner with headline, subtitle, image/placeholder, and call-to-action button | 2 | 2 | 0 | Hero content and image/banner asset | Build the main Home Page hero area with proper spacing, alignment, typography, and button styling.
Complete | Implement Featured Categories or Product Preview section | Arnob Intishar Chisty | Category cards or product preview cards based on the wireframe | 2 | 2 | 0 | Category/product names and images/placeholders | Create reusable Home Page card layout only; this is not the full Product Page.
Complete | Implement Home Page information/content sections | Maria Islam Bushra | About/brand section, promotional section, call-to-action section, newsletter or contact section | 2 | 2 | 0 | Home Page text content | Convert remaining wireframe sections into frontend code with consistent spacing, fonts, titles, and button styles.
Complete | Implement Footer section | Maria Islam Bushra | Footer with links, contact information, social placeholders, and copyright text | 3 | 3 | 0 | Footer content and social/contact information | Footer should match the Home Page wireframe and remain clean, simple, and responsive.
Complete | Apply responsive styling for Home Page | Maria Islam Bushra | Responsive Home Page layout for desktop, tablet, and mobile | 3 | 3 | 0 | Team review | Check spacing, card layout, header behavior, image scaling, and section alignment across screen sizes.
Complete | Review, test, and finalize Home Page implementation | Arnob Intishar Chisty | Home Page review checklist, bug notes, final Sprint 1 update | 2 | 2 | 0 | Implemented Home Page code | Review match to wireframe, navigation appearance, responsiveness, content placement, and layout consistency.
Summary of Hours |  | Assigned To | Estimated | Spent | Remaining
|  | Arnob Intishar Chisty | 8 | 8 | 0
|  | Nazeefa Binta Alam | 8 | 8 | 0
|  | Maria Islam Bushra | 8 | 8 | 0

## Sprint 2
Sprint 2 Work Distribution — Product Listing and Product Details
Sprint 2 Goal: | Implement the Product Listing and Product Details features based on the approved wireframe. The team will create the Django REST backend foundation, Product and Category data models, Repository Pattern, product API endpoints, responsive Product Listing page, filtering controls, and Product Details page. The React frontend will retrieve product information from the Django API.
Sprint 2 Scope: | Screen 02 Product Listing page; Screen 03 Product Details page; Django REST backend foundation; Product and Category database models; Repository Pattern; Product-related REST API endpoints; React and Django API integration; Responsive styling and testing. Do not include Cart, Checkout, Payment, Orders, Authentication, Admin Dashboard, Customer management, or Deployment. Add to Cart and Buy Now buttons are frontend placeholders only during Sprint 2.
Status | Task | Assigned To | Deliverable | Time Estimated | Time Spent | Time Remaining | Support Required | Notes
Complete | Review the Product Listing and Product Details wireframes and prepare the Sprint 2 implementation plan | Arnob Intishar Chisty | Wireframe section breakdown, technical requirements, component list, API requirements, and implementation checklist | 2 | 0 | 2 | Approved Product Listing and Product Details wireframes | Identify the shared header, filter sidebar, product grid, reusable product cards, product image gallery, product information, size selector, color selector, quantity control, Add to Cart placeholder, and Buy Now placeholder.
Complete | Set up the Django REST backend structure | Arnob Intishar Chisty | Django project, store application, Django REST Framework configuration, CORS configuration, URLs, and backend folder structure | 3 | 0 | 3 | Python, Django, and frontend project structure | Prepare the backend foundation inside the existing backend folder. Follow the MVC/MVT architecture by separating models, API views, serializers, URLs, and frontend presentation.
Complete | Implement the Repository Pattern for product and category data | Arnob Intishar Chisty | ProductRepository and CategoryRepository classes | 2 | 0 | 2 | Completed Product and Category models | Repository classes should handle product listing, product details, featured products, category filtering, and product search queries. Database query logic must remain separate from API views.
Complete | Review, test, and finalize the Sprint 2 implementation | Arnob Intishar Chisty | Sprint 2 testing checklist, bug report, completed fixes, and review notes | 1 | 0 | 1 | Completed frontend and backend implementation | Test the product APIs, frontend-backend connection, search, filters, product-card navigation, Product Details content, responsiveness, loading states, empty states, and API-error states.
Complete | Prepare product content, categories, options, and image assets | Nazeefa Binta Alam | Product names, categories, prices, descriptions, product images or placeholders, sizes, colors, stock values, and filter labels | 2 | 0 | 2 | Wireframe and approved branding direction | Prepare realistic product information for the Product Listing and Product Details pages. Content should include enough products to demonstrate the product grid and filters.
Complete | Implement the Product Listing page from the wireframe | Nazeefa Binta Alam | Responsive Product Listing page with shared header, page title, filter sidebar, sorting control, product grid, and reusable product cards | 3 | 0 | 3 | Product content, Product API, and approved wireframe | Each product card should contain a product image, product name, short description or category, and price. The desktop layout should match the wireframe, while tablet and mobile layouts should reorganize the sidebar and product grid appropriately.
Complete | Implement product search, sorting, and filtering | Nazeefa Binta Alam | Product search field, category filter, price-range filter, size filter, color filter, sorting control, reset option, and empty-result message | 3 | 0 | 3 | Product and Category API data | Users should be able to search products by name, filter products using the sidebar options shown in the wireframe, sort the results, clear the filters, and see a clear message when no products match.
Complete | Create Product and Category database models | Maria Islam Bushra | Django Product and Category models, model relationships, migrations, and Django admin registration | 2 | 0 | 2 | Final product-data requirements | Product fields should include name, category, description, price, primary image, additional images or image placeholders, available sizes, available colors, stock quantity, featured status, and created date.
Complete | Create serializers and product-related REST API endpoints | Maria Islam Bushra | Product and Category serializers, API views, URL routes, API responses, and basic API testing | 3 | 0 | 3 | Product models and repository classes | Implement API endpoints for all products, individual product details, categories, featured products, search, and filtering. API views should use repository classes instead of containing direct database-query logic. Required API endpoints: GET /api/products/; GET /api/products/{id}/; GET /api/categories/; GET /api/products/featured/. The products endpoint should support query parameters where possible: ?search= ?category= ?min_price= ?max_price= ?size= ?color= ?ordering=
Complete | Implement the Product Details page and connect it to the API | Maria Islam Bushra | Responsive Product Details page with API data, large product image, four image thumbnails, product name, price, description, size selector, color selector, quantity control, Add to Cart placeholder, and Buy Now placeholder | 3 | 0 | 3 | Product Details API endpoint, product content, and approved wireframe | Clicking a product card on the Product Listing page should open the correct Product Details page. Add to Cart and Buy Now should be visible but should not implement cart, checkout, payment, or order functionality during Sprint 2.
Summary of Hours |  | Assigned To | Estimated | Spent | Remaining
|  | Arnob Intishar Chisty | 8 | 0 | 8
|  | Nazeefa Binta Alam | 8 | 0 | 8
|  | Maria Islam Bushra | 8 | 0 | 8
|  | Total | 24 | 0 | 24
Note:
Definition of Done
Django backend runs successfully.
Product and Category migrations run without errors.
Repository Pattern separates database-query logic from API views.
Product and Category APIs return valid JSON.
React successfully retrieves products from the Django API.
Product Listing page displays API product data.
Search, filters, sorting, and reset controls work.
Product cards open the correct Product Details page.
Product Details page displays the correct API data.
Loading, empty-result, missing-product, and API-error states are handled.
Desktop, tablet, and mobile layouts work correctly.
Frontend linting and production build pass.
Backend tests and Django system checks pass.
Sprint 2 checklist and review notes are documented.

## Sprint 3
Sprint 3 Work Distribution — Authentication, Cart, Checkout, and Orders
Sprint 3 Goal: | Implement user authentication, shopping cart, checkout, and order-placement functionality for the NazRiy e-commerce website. Connect the React frontend to the Django REST backend.
Status | Task | Assigned To | Deliverable | Time Estimated | Time Spent | Time Remaining | Support Required | Notes
Complete | Review the Cart and Checkout wireframe and prepare the Sprint 3 implementation plan | Arnob Intishar Chisty | Component list, API requirements, technical plan, and checklist | 1 | 0 | 1 | Approved wireframe and completed Sprint 2 | Identify cart items, quantity controls, order summary, delivery form, and checkout flow.
Complete | Implement frontend cart state management and persistence | Arnob Intishar Chisty | Add, remove, update, and persist cart items | 3 | 0 | 3 | Completed Product Details page | Cart contents and navbar count should remain available after refreshing.
Complete | Build the responsive Cart and Checkout page | Arnob Intishar Chisty | Cart items, quantity controls, removal button, totals, and order summary | 3 | 0 | 3 | Cart state and approved wireframe | Match Screen 04 on desktop and adapt it for tablet and mobile.
Complete | Review, test, and finalize Sprint 3 integration | Arnob Intishar Chisty | Testing checklist, bug report, fixes, and review notes | 1 | 0 | 1 | Completed frontend and backend implementation | Test authentication, cart, checkout, totals, validation, APIs, and responsiveness.
Complete | Build registration and login pages | Nazeefa Binta Alam | Responsive registration and login forms | 2 | 0 | 2 | Authentication API | Include validation, loading indicators, errors, and successful-login feedback.
Complete | Create the checkout delivery-information form | Nazeefa Binta Alam | Name, email, phone number, address, city, postal code, and validation | 3 | 0 | 3 | Cart and order requirements | Clearly identify required fields and prevent invalid submission.
Complete | Implement loading, empty-cart, error, and order-success states | Nazeefa Binta Alam | Complete feedback states for cart and checkout | 3 | 0 | 3 | Cart and Order APIs | Include an empty-cart message, API error messages, submission loading, and order confirmation.
Complete | Create authentication APIs | Maria Islam Bushra | Registration, login, logout, and current-user endpoints | 2 | 0 | 2 | Django REST Framework | Secure protected endpoints and return appropriate HTTP responses.
Complete | Create Cart, CartItem, Order, and OrderItem models | Maria Islam Bushra | Models, relationships, migrations, and admin registration | 3 | 0 | 3 | Product and User models | Store quantities, prices, totals, customer information, status, and creation date.
Complete | Create cart and order REST API endpoints | Maria Islam Bushra | Cart CRUD, checkout, order creation, and user-order endpoints | 3 | 0 | 3 | Cart and Order models | Validate product stock and calculate totals on the backend.
Summary of Hours |  | Assigned To | Estimated | Spent | Remaining
|  | Arnob Intishar Chisty | 8 | 0 | 8
|  | Nazeefa Binta Alam | 8 | 0 | 8
|  | Maria Islam Bushra | 8 | 0 | 8
|  | Total | 24 | 0 | 24
Note:
Definition of Done
Registration, login, logout, and protected routes work.
Users can add products to the cart.
Navbar displays the correct cart quantity.
Users can update quantities and remove products.
Cart contents persist after refreshing.
Subtotal, delivery charge, and total calculate correctly.
Checkout validates required delivery information.
Orders are saved in the database.
Product stock is validated before order creation.
Loading, empty, error, and success states work.
Frontend communicates successfully with the Django API.
Desktop, tablet, and mobile layouts work.
Frontend linting and production build pass.
Django system checks, migrations, and backend tests pass.
Sprint 3 checklist and review notes are documented.

## Sprint 4
Sprint 4 Work Distribution — Post-Purchase, Administration, Security, and Deployment
Sprint 4 Goal: | Complete the post-purchase experience, order management, administration workflow, security improvements, deployment readiness, and final quality assurance for the NazRiy e-commerce website. Finalize the React + TypeScript + Vite frontend integration with the Django REST Framework backend.
Status | Task | Assigned To | Deliverable | Time Estimated | Time Spent | Time Remaining | Support Required | Notes
Complete | Review Sprint 4 requirements and prepare the implementation plan | Arnob Intishar Chisty | Component list, API requirements, technical plan, risks, and checklist. | 1 | 0 | 1 | Completed Sprint 3 features, approved requirements, and team availability | Map frontend components, backend endpoints, dependencies, security risks, deployment requirements, and the final testing sequence.
Complete | Build the responsive customer order-history page | Arnob Intishar Chisty | Order list, order details, item summaries, totals, dates, and status indicators. | 3 | 0 | 3 | Protected user order APIs and completed Sprint 3 order data | Display only the authenticated customer's orders and provide clear navigation to full order details across desktop, tablet, and mobile.
Complete | Implement protected frontend routes and authenticated-session restoration | Arnob Intishar Chisty | Route protection, expired-token handling, current-user restoration, and login redirects. | 2 | 0 | 2 | Authentication API, token strategy, and current-user endpoint | Protect profile and order routes, restore sessions safely after refresh, and preserve the user's intended destination after login.
Complete | Review, test, and finalize Sprint 4 integration | Arnob Intishar Chisty | Testing checklist, bug report, fixes, build verification, and Sprint 4 review notes. | 2 | 0 | 2 | Completed frontend, backend, administration, and deployment work | Verify authentication, order ownership, profile updates, status changes, inventory, accessibility, responsive layouts, builds, and deployment checks.
Complete | Build the customer profile and account page | Nazeefa Binta Alam | Profile details, editable name/email fields, validation, loading, success, and error feedback. | 3 | 0 | 3 | Profile and password-management APIs | Keep account details responsive and clearly distinguish editable fields, validation messages, submission loading, and successful updates.
Complete | Create responsive order-tracking and order-detail interfaces | Nazeefa Binta Alam | Order status timeline, delivery details, ordered items, payment summary, and mobile layout. | 3 | 0 | 3 | Order detail and order-status APIs | Use consistent status labels and present delivery information, items, quantities, prices, totals, and progress clearly on all screen sizes.
Complete | Improve accessibility and user-feedback states | Nazeefa Binta Alam | Keyboard navigation, accessible labels, focus handling, empty states, loading states, and error messages. | 2 | 0 | 2 | Completed Sprint 4 customer-facing interfaces | Test logical tab order, visible focus, form labels, screen-reader-friendly messages, route changes, empty results, and API failures.
Complete | Create profile and password-management APIs | Maria Islam Bushra | Current-user profile update and secure password-change endpoints. | 2 | 0 | 2 | Existing authentication and current-user functionality | Validate profile fields, require secure password confirmation rules, protect endpoints, and return appropriate success and error responses.
Complete | Create order-detail and order-status APIs | Maria Islam Bushra | Protected user order list/detail endpoints and validated order-status responses. | 2 | 0 | 2 | Order, OrderItem, User models, and authentication permissions | Enforce order ownership, serialize complete delivery and item data, validate statuses, and prevent access to another user's orders.
Complete | Build staff order-management and inventory workflows | Maria Islam Bushra | Admin order filtering, status updates, stock monitoring, and admin registration/configuration. | 3 | 0 | 3 | Django admin, order models, product stock fields, and staff permissions | Provide practical filters, safe status transitions, useful admin list displays, and accurate inventory visibility without exposing customer-only actions.
Complete | Add backend security, deployment checks, and automated tests | Maria Islam Bushra | Permission tests, ownership tests, validation tests, environment configuration, and deployment checklist. | 1 | 0 | 1 | Completed Sprint 4 APIs, deployment target, and environment requirements | Cover authentication failures, object ownership, invalid updates, environment variables, database compatibility, static assets, and production-readiness checks.
Summary of Hours |  | Assigned To | Estimated | Spent | Remaining
|  | Arnob Intishar Chisty | 8 | 0 | 8
|  | Nazeefa Binta Alam | 8 | 0 | 8
|  | Maria Islam Bushra | 8 | 0 | 8
|  | Total | 24 | 0 | 24
Note: | Project directory: D:\NazRiy ¦ Technology: React + TypeScript + Vite frontend; Django REST Framework backend; SQLite/PostgreSQL-compatible database.

## Sprint 5
NazRiy E-Commerce Website — Sprint 5 Work Plan
Automated Testing, Payment Workflow, CI/CD, UAT, and Production Release Preparation
Sprint 5 Goal: | Improve release confidence by adding isolated unit tests, sandbox payment-status handling, continuous integration, user acceptance testing, and final production-release checks for the React + TypeScript + Vite frontend and Django REST Framework backend.
Status | Task | Assigned To | Deliverable | Estimated Hours | Time Spent | Time Remaining | Support Required | Notes
Complete | Review Sprint 5 requirements and prepare the automated-testing strategy | Arnob Intishar Chisty | Testing scope, test pyramid, critical workflows, tools, risks, and checklist. | 1 | 1 | 0 | Completed Sprint 1–4 features, existing test suite, and approved Sprint 5 scope | Define unit, component, API/integration, and UAT coverage; target at least 80% coverage for critical business-logic modules.
Complete | Configure frontend unit-testing infrastructure using Vitest, React Testing Library, jsdom, and coverage reporting | Arnob Intishar Chisty | Test configuration, setup file, npm test scripts, mocks, and coverage command. | 2 | 2 | 0 | Frontend repository, package manager, component architecture, and CI-compatible scripts | Configure deterministic mocks and isolated test environments without relying on live external services.
Complete | Write frontend unit tests for cart state, authentication restoration, protected routes, and order-history behaviour | Arnob Intishar Chisty | Isolated tests for cart calculations, persistence, token handling, redirects, loading, empty, and error states. | 3 | 3 | 0 | Cart utilities, localStorage logic, authentication context, route guards, and order APIs | Cover cart totals, persistence, token expiry, session restoration, protected routing, and order-history feedback states.
Complete | Run integration regression testing and finalize Sprint 5 technical review | Arnob Intishar Chisty | Regression report, bug fixes, frontend lint/build results, backend test results, and final review notes. | 2 | 2 | 0 | Completed Sprint 5 frontend, backend, payment, testing, and CI work | Recheck browse-to-order workflows, authentication, ownership, payment status, accessibility, builds, and deployment checks.
Complete | Build the sandbox payment and order-confirmation user interface | Nazeefa Binta Alam | Payment-method selection, payment status, loading, failure, retry, cancellation, and success interfaces. | 3 | 3 | 0 | Sandbox or mock payment provider contract and backend payment-status API | Use sandbox/mock processing only; do not process real customer money without approved production credentials.
Complete | Improve accessibility, responsiveness, and feedback states for checkout and payment pages | Nazeefa Binta Alam | Form labels, keyboard navigation, focus states, mobile layout, accessible error messages, and status announcements. | 2 | 2 | 0 | Completed checkout and sandbox payment interfaces | Validate desktop, tablet, and mobile layouts; provide visible focus and screen-reader-friendly status feedback.
Complete | Write frontend component tests for registration, login, profile, checkout, and payment interfaces | Nazeefa Binta Alam | React Testing Library tests for validation, submission, loading, error, and success states. | 2 | 2 | 0 | Vitest, React Testing Library, jsdom, mocks, and completed user-facing components | Test user interactions and accessible outcomes rather than implementation details.
Complete | Conduct user acceptance testing and prepare client-facing usage evidence | Nazeefa Binta Alam | UAT checklist, screenshots, identified issues, acceptance results, and short user guide. | 1 | 1 | 0 | Stable staging build, agreed acceptance scenarios, and representative test data | Document browse → cart → login → checkout → sandbox payment → confirmation → tracking evidence.
Complete | Implement the backend sandbox payment workflow and payment-status management | Maria Islam Bushra | Payment model or fields, validated payment endpoint, pending/paid/failed/cancelled states, duplicate-request protection, and admin visibility. | 3 | 3 | 0 | Order models, checkout totals, authentication permissions, and sandbox provider requirements | Validate totals and order ownership on the backend; keep payment and order states consistent and prevent duplicate submissions.
Complete | Add backend unit tests and API regression tests | Maria Islam Bushra | Django TestCase tests for models, serializers, validation, payment logic, stock behaviour, permissions, ownership, and invalid requests. | 3 | 3 | 0 | Django TestCase, DRF APITestCase, deterministic fixtures, and existing 17 API/integration tests | Expand comprehensive backend unit coverage while retaining authentication, stock, permission, and ownership regression checks.
Complete | Configure GitHub Actions continuous integration | Maria Islam Bushra | CI workflow that runs backend tests, frontend unit tests, lint, production build, migration check, and Django system check. | 1 | 1 | 0 | GitHub repository, repeatable install commands, environment variables, and test scripts | Failed checks must block pull-request merging until corrected.
Complete | Finalize production configuration, logging, backup, rollback, and release checklist | Maria Islam Bushra | Deployment checklist, environment-variable review, database backup steps, rollback steps, and operational notes. | 1 | 1 | 0 | Staging environment, deployment target, database procedures, and release ownership | Confirm logging, HTTPS, CSRF/CORS, no pending migrations, backup validation, rollback sequence, and production-readiness checks.
Summary of Hours |  | Assigned To | Estimated | Spent | Remaining
|  | Arnob Intishar Chisty | 8 | 8 | 0
|  | Nazeefa Binta Alam | 8 | 8 | 0
|  | Maria Islam Bushra | 8 | 8 | 0
|  | Total | 24 | 24 | 0